## Slide 1
LEGAL SAATHI
From Idea → Architecture → Parallel Build → AI-Assisted Execution
4 Developers • One Architecture • One Shared Execution Plan
Citizen
→
AI Pipeline
→
Legal Knowledge
→
Verified Answer
→
Action
→
Collective Intelligence
TEAM EXECUTION MEETING • This deck is your blueprint for how we build Legal Saathi as a 4-person engineering team.
Multilingual AI Legal Assistance | Grounded in Real Indian Law | Voice + Text | Privacy-First Collective Action
Notes: Welcome everyone. This is not a product pitch — this is our engineering execution plan. By the end of this meeting, each of you will know exactly what you own, what files you touch, how you use AI tools, and what we build first. Let's align and then start building.

## Slide 2
PRODUCT DIFFERENTIATION
We are not building another legal chatbot.
02
GENERIC AI CHATBOT
✖ Generic answers from LLM internal training — no verifiable source.
✖ Zero citations a guess and a fact look identical to the user.
✖ Information dead-end conversation ends at text; no action pathway.
✖ No case memory every session is ephemeral, forgotten on reload.
✖ Users stay isolated community-wide legal patterns go undetected.
✖ English-only excludes 90%+ of Indian citizens who need help.
LEGAL SAATHI
✔ Hybrid Retrieval ChromaDB (vector) + BM25 (lexical) over real Acts & Judgments.
✔ Claim-to-Source Citations every claim maps to an Act/Section + Confidence Badge.
✔ Action Modules Evidence Checklist, Legal Notice draft, RTI form generation.
✔ Structured Case Schema persisted entities, dates, amounts, opposing party.
✔ Legal Saathi Engine privacy-first pattern detection + collective action.
✔ Voice-First & Multilingual Hindi/Tamil/English voice round-trip for real citizens.
The LLM is NEVER the source of truth — it synthesizes retrieved legal evidence.
Notes: This is the core thesis. Every other legal chatbot lets the AI hallucinate answers. We don't. Our system retrieves real Indian statutory law and judgments first, then uses the LLM only to synthesize and explain what was retrieved. The LLM never invents legal claims. This is what makes Legal Saathi trustworthy.

## Slide 3
USER EXPERIENCE
ASK → UNDERSTAND → VERIFY → EXPLAIN → ACT → UNITE
03
01
ASK
Voice / Text
Regional Language
→
02
UNDERSTAND
Intent Classifier
+ Entity Extraction
→
03
VERIFY
ChromaDB + BM25
Hybrid Legal Search
→
04
EXPLAIN
Grounded Answer
+ Citation + Badge
→
05
ACT
Evidence Checklist
Legal Notice / RTI
→
06
UNITE
Similarity → Pattern
Consent → Collective
★ Core Differentiator
PRINCIPLES: Trust · Evidence · Transparency · Action · Multilingual Accessibility · Privacy · Modularity
Notes: This is the complete citizen journey. A citizen describes their legal problem in their own language — voice or text. The system extracts structured facts, searches real legal databases, generates a cited answer with a confidence badge, offers concrete actions like a legal notice or evidence checklist, and then — this is the magic — the Legal Saathi Engine checks if this pattern matches other complaints for potential collective action.

## Slide 4
CORE ARCHITECTURAL PRINCIPLE
The LLM is NOT our source of truth.
04
✖ THE WRONG WAY
User Question
↓
LLM (Hallucination)
↓
Unverified Answer
✖
✔ THE LEGAL SAATHI WAY
User Question
↓
Intent Classification
↓
Legal Retrieval (ChromaDB + BM25)
↓
Evidence Context Assembly
↓
LLM Synthesizes Retrieved Evidence
↓
Citation Verification + Confidence Badge
Legal retrieval is the source of truth. The LLM only explains what was retrieved.
THIS IS THE SLIDE JUDGES MUST UNDERSTAND: Retrieval-first, LLM-second, citation-always.
Notes: This is our most important architectural principle and the slide you should spend time on. Show the wrong way — LLM directly answering legal questions — and then show our way. The key insight is that legal retrieval via ChromaDB and BM25 is the source of truth. The LLM only synthesizes and explains what was retrieved. Every claim is checked against the source. This is what makes us trustworthy, not just another wrapper around GPT.

## Slide 5
SYSTEM DESIGN
Inside Legal Saathi — Layered & Independently Replaceable
05
CLIENT LAYER
Next.js 14 • TypeScript • Tailwind • Framer Motion • Voice UI
Owner: T1 & T4
↓
API & ORCHESTRATION
FastAPI • Auth • Safety • Pipeline • Intent Classifier
Owner: T2
↓
HYBRID RAG & AI
ChromaDB • BM25 • Reciprocal Rank Fusion • LLM • Citation Layer
Owner: T3 & T2
↓
LEGAL SAATHI ENGINE
Entity Extraction • Normalization • Similarity • Clustering • Consent
Owner: T3
↓
ACTION & INFRASTRUCTURE
Evidence Checklist • Legal Notice • RTI • Docker • CI/CD • E2E
Owner: T4
Each layer interacts via frozen contracts (docs/API_CONTRACT.md & docs/CASE_SCHEMA.md). Swap any layer without breaking the system.
Notes: Walk through each layer from top to bottom. Emphasize that each layer is independently replaceable — if we want to swap ChromaDB for another vector DB later, only T3's retrieval_service.py changes. The frozen API contract and Case Schema are the glue that holds all layers together.

## Slide 6
TEAM ORGANIZATION
Four developers. Four ownership zones. One system.
06
T1
Frontend & UI
· Next.js 14 App Router + Pages
· Chat UI / CitationCard / ConfidenceBadge
· Case Workspace & Action Forms
· TypeScript API Client (mock → real)
· Loading / Error / Empty states
T2
Backend & Orchestration
· FastAPI Routers & Middleware
· pipeline.py orchestration flow
· classifier.py + emergency routing
· LLM abstraction + provider fallback
· Citation logic + session auth
T3
Data, RAG & Engine
· Corpus ingestion & chunking
· ChromaDB + BM25 + Rank Fusion (RRF)
· Case Schema contract (OWNER)
· Legal Saathi Engine: similarity
· Golden query evaluation set
T4
Voice, Actions & DevOps
· Docker Compose + CI/CD pipeline
· Action Modules: Checklist / Notice / RTI
· Voice STT → pipeline → TTS
· E2E integration test suite
· Security audit & PR gatekeeper
Each developer has a clear, non-overlapping ownership zone. No ambiguity about who owns what.
Notes: Introduce each teammate's zone. The key message is no overlapping ownership and no ambiguity. T1 never touches backend/. T2 never edits retrieval_service.py internals. T3 owns the Case Schema contract. T4 is the infrastructure and quality gatekeeper. Everyone knows their boundary.

## Slide 7
OWNERSHIP MATRIX
Who owns what? One clean table.
07
Domain
T1
T2
T3
T4
Frontend UI/UX
LEAD
Review
—
QA
API & Orchestration
Client
LEAD
Service
—
Hybrid RAG (Chroma+BM25)
—
Consume
LEAD
—
Case Schema Contract
Types
Model
OWNER
Seed
Citation & Trust Layer
Badge
LEAD
Metadata
Review
Legal Saathi Engine
UI
API
LEAD
Privacy
Action Modules
Forms
API
Taxonomy
LEAD
Voice (STT / TTS)
Audio
Hooks
—
LEAD
Docker / CI/CD
—
Package
Volume
LEAD
E2E & Security Testing
FE Test
BE Test
RAG Test
LEAD
LEAD = Primary owner. OWNER = Contract authority. Others = Review / Consume / Support.
Notes: Don't read every cell — just highlight the pattern. Each row has exactly one LEAD or OWNER. That person makes decisions for that domain. Others consume, review, or support. Point out that T3 OWNS the Case Schema — that means if anyone needs a schema change, they go through T3 and the team sync process.

## Slide 8
EXECUTION STRATEGY
We do NOT build sequentially.
08
✖ BAD WORKFLOW
T1 waits for T2's API
T2 waits for T3's RAG
T3 waits for T4's infra
Everyone is blocked
✖
✔ PARALLEL EXECUTION
T1 → Mock API → Full UI
T2 → Mock RAG → Full Backend
T3 → Corpus → Full RAG Index
T4 → Docker + CI → Actions + Voice
BUILD IN PARALLEL. INTEGRATE THROUGH CONTRACTS.
Frontend uses mock API fixtures • Backend uses mock retrieval service • RAG builds independently • DevOps sets up infra from hour 1
MOCKING RULE: Mocks live in __mocks__/ or fixtures/ — never inline. Swapping mock → real = 1 import change.
Notes: This is a critical cultural slide. In hackathons, the number one failure mode is sequential blocking — everyone waits on someone else. We eliminate this by coding against frozen contracts and mock fixtures from Day 1. T1 builds the entire chat UI against a mock API. T2 builds the entire pipeline against a mock retrieval service. T3 builds the RAG index independently. T4 sets up Docker and CI without waiting for anyone. Integration happens AFTER contracts are stable.

## Slide 9
SHARED CONTRACTS
Our shared contracts are the foundation of parallel execution.
09
docs/CASE_SCHEMA.md + docs/API_CONTRACT.md
Frozen in Phase 1 — the source of truth for all 4 teammates
T1 Frontend
Builds TypeScript types
from CASE_SCHEMA.
Mocks API responses
from API_CONTRACT.
↓
T2 Backend
Implements routers
matching API_CONTRACT.
Consumes Case schema
as Pydantic models.
↓
T3 RAG / Engine
OWNS CASE_SCHEMA.
Exposes retrieval_service
matching the contract.
Golden query evaluation.
↓
T4 Integration
Tests against contracts.
Action templates from
CASE_SCHEMA structure.
E2E contract validation.
↓
⚠ SHARED CONTRACTS ARE NOT CHANGED CASUALLY. Any change to CASE_SCHEMA.md or API_CONTRACT.md requires a live sync with all 4 developers first.
Notes: The contracts are what make parallel work possible. If everyone agrees on the shape of the Case object and the API response formats BEFORE coding, then everyone can build independently. T3 owns the Case Schema — any changes go through the team sync process described in Part 15 of the roadmap. This is not bureaucracy — it's the cheapest insurance against integration nightmares.

## Slide 10
AI-ASSISTED DEVELOPMENT
AI is our fastest developer — not our architect.
10
HUMAN DECIDES
Architecture & Design — system structure, layer boundaries, data flow
Shared Contracts — CASE_SCHEMA.md, API_CONTRACT.md
Security & Privacy — consent flows, PII handling, emergency routing
Business Rules — what legal logic is correct, what's wrong
Code Review — inspect every diff before committing
Integration Decisions — when to swap mock → real
AI IMPLEMENTS
Boilerplate & Scaffolding — routers, components, config files
Feature Implementation — from task spec to working code
Unit & Integration Tests — pytest, component tests, E2E scripts
Refactoring — within your own owned files only
Documentation — docstrings, README, inline comments
Debugging — trace errors, fix type mismatches
→
WORKFLOW: Human → Prompt with Context → AI Writes Code → AI Writes Tests → Human Reviews Diff → Commit
Notes: Vibe coding does NOT mean blindly pasting AI output. Humans are the architects and tech leads. AI is our fast junior developer. Humans decide architecture, contracts, security, and what's correct. AI writes the implementation, tests, and documentation. Every AI-generated change gets a human diff review before committing. This is how we move fast without breaking things.

## Slide 11
ENGINEERING COMMANDMENTS
6 rules that keep AI-assisted development safe.
11
01
Never let AI invent schemas
All data models must follow
docs/CASE_SCHEMA.md &
docs/API_CONTRACT.md
02
One Task ID per session
Prompt for CORE-009, not
'build the backend'.
Keep context atomic.
03
Always provide context files
Give AI your Master Prompt +
blueprint + task definition
at session start.
04
Never touch teammate's files
T1 doesn't edit backend/.
T2 doesn't edit scripts/.
AI inspects first.
05
Tests + build before done
AI writes unit tests.
Not done until pytest /
npm run build passes.
06
Contracts need live sync
Zero tolerance for silent
schema changes. Sync with
all 4 devs first.
These laws are non-negotiable. Violating any one of them will cause integration failures and wasted time.
Notes: Go through each law briefly. Law 1 and Law 6 are the most critical — if AI invents a schema field that doesn't match the contract, it creates a type mismatch that wastes hours to debug. Law 2 keeps AI sessions focused — never ask it to build an entire system in one prompt. These are battle-tested rules for AI-assisted team development.

## Slide 12
DAILY WORKFLOW
Every developer follows the same loop — every task, every day.
12
1
Pull develop
git pull develop
→
2
Branch
feature/TASK-ID-name
→
3
Feed AI context
Master Prompt + docs + task
↓
4
AI implements
Code + unit tests
5
Run tests/build
pytest / npm run build
←
6
Review + PR
git diff → commit → PR
←
git checkout -b feature/core-009-pipeline-orchestration
[CORE-009] Implement pipeline orchestration with LLM fallback
Notes: Walk through the loop step by step. Emphasize that EVERY task follows this exact sequence — no exceptions. Step 3 is critical: always give the AI your Master Prompt plus the relevant blueprint sections plus the specific task definition of done. Step 5 is non-negotiable: code is not done until tests pass. Step 6: always review the git diff with your own eyes before committing.

## Slide 13
EXECUTION TIMELINE
From repository audit to working demo — Phase 0 through 10.
13
0
Audit
All
Phase 0
1
Freeze
All
Phase 1
2
Skeletons
Parallel
Phase 2
3
Case+Corpus
T2+T3
Phase 3
4
Grounded MVP
T2+T3
CRITICAL
Phase 4
5
Workspace
T1+T4
Phase 5
6
Notice/RTI
T4
Phase 6
7
Voice+Engine
T4+T3
Phase 7
8
Collective
T3+T1
Phase 8
9
Test+Sec
All
Phase 9
10
Demo
All
Phase 10
Foundation
Core
Critical Path
Expansion
Advanced
PHASE 4 IS THE LINCHPIN User Question → Intent → Legal Retrieval → Grounded Answer → Citation → Confidence Badge
If Phase 4 slips → stop adding features → cut P2 scope immediately. First make the core trustworthy. Then make it bigger.
Notes: Walk through the timeline left to right. Foundation phases are fast — audit and freeze in the first 1-2 days. Phases 2-3 are skeleton work that runs in parallel. Then zoom into Phase 4 — this is where the magic happens. Phase 4 is the first time a real user question produces a real cited answer. Everything downstream depends on this. If Phase 4 timeline slips, we immediately cut P2 features. We never add scope that delays the critical path.

## Slide 14
CRITICAL PATH
Everything depends on one milestone.
14
User Question
↓
Intent Classification
↓
Legal Retrieval (ChromaDB + BM25)
↓
Evidence Context Assembly
↓
LLM Synthesizes Evidence
↓
Citation Verification
↓
Confidence Badge
MILESTONE 1
Grounded Answer
IF THIS SLIPS
Stop adding features. Cut P2 scope immediately.
First make the core trustworthy. Then make it bigger. Never let a P2 feature touch the critical path.
Notes: This is the single most important execution slide. Zoom in on the flow. Legal Retrieval — that amber-highlighted layer — is the source of truth. The LLM only synthesizes what was retrieved. The citation layer verifies claims against sources. The confidence badge tells the user how reliable the answer is. If this pipeline doesn't work, nothing else matters — not voice, not the Engine, not action modules. Protect Phase 4 above all else.

## Slide 15
DEMO STORY & IMMEDIATE ACTIONS
What we will demonstrate + what you do today.
15
THE 90-SECOND DEMO STORY
1. Voice Input (Hindi) Citizen: "Mera makaan maalik deposit wapas nahi kar raha."
2. Case Extraction Issue: Tenancy | Amount: INR 40K | Opponent: Landlord
3. Hybrid Legal Search ChromaDB + BM25 retrieves Model Tenancy Act sections
4. Cited Answer + Badge GREEN [STRONG EVIDENCE] + Section 13(2) citation
5. Action Generation Evidence Checklist + 1-Click Legal Notice Draft
6. Engine Pattern "4 similar cases nearby" → Consent → Collective Notice
"It turns a legal problem into a sourced answer and an action — and it notices when you're not alone."
TODAY'S COMMITMENT
T1
Audit frontend/ components
T2
Audit backend/ + pipeline.py
T3
Audit RAG setup + gather Acts
T4
Build docker-compose + CI
END-OF-DAY GOAL
Commit AUDIT_RESULTS.md Freeze CASE_SCHEMA.md and API_CONTRACT.md Phase 2 begins tomorrow!
Notes: Two things on this slide. First, walk through the demo story — this is the exact scenario we'll present to judges. A Hindi-speaking citizen with a deposit problem gets a cited answer, an evidence checklist, a legal notice draft, and discovers 4 other tenants with the same issue. Second, give everyone their immediate action item. By end of today, we need the audit done and contracts frozen so Phase 2 parallel work can start tomorrow.

## Slide 16
OUR DEVELOPMENT CONTRACT
One architecture.
Four owners.
Parallel execution.
AI-assisted implementation.
Human-controlled decisions.
—————————
Build fast.
Integrate carefully.
Never sacrifice trust.
LEGAL SAATHI — LET'S BUILD.
Notes: This is the closing slide. Read the manifesto aloud — slowly. One architecture. Four owners. Parallel execution. AI-assisted implementation. Human-controlled decisions. Then pause. Build fast. Integrate carefully. Never sacrifice trust. Then end with: Legal Saathi — let's build. The meeting is over. Everyone goes to their Phase 0 audit immediately.